VillaOps

Milestone, Phase & MVP Plan

v2.0  ·  May 2026  ·  Revised with Setup Option B (minimal Settings UI in Week 1)

| Change from v1.0 | Property setup (Settings UI Option B) added to Week 1 alongside auth. MVP extended from 10 to 12 weeks. All milestones re-sequenced accordingly. |
| --- | --- |
| Total phases | 3 phases — MVP · Phase 1 · Phase 2 |
| MVP duration | 12 weeks (was 10 in v1.0) — extra 2 weeks absorb Settings UI build in Week 1 |
| MVP go-live | End of Month 3 (Week 12) — one pilot property fully live, paper process retired |
| Phase 1 GA | Month 7–8 — all 9 modules, all 5 properties, all 7 roles |
| Phase 2 GA | Month 18 — mobile app, guest-facing features, internal CM integration |

# 1. What Changed from v1.0

The core phasing strategy (MVP → Phase 1 → Phase 2) and all feature scope remain identical to v1.0. The only change is that property setup — previously a gap — is now formally included in the MVP as Option B: a minimal Settings UI built in Week 1 alongside authentication. This adds approximately 2 weeks to the MVP timeline and shifts all subsequent milestones accordingly.

| Area | v1.0 (old) | v2.0 (revised) |
| --- | --- | --- |
| Property setup | Missing — assumed but not planned | Week 1 — minimal Settings UI (Option B), built alongside auth |
| Week 0 content | Kick-off, tools, environments, design system | Same + data collection: ops champion supplies room list, rate plans, CM credentials |
| Week 1 content | Auth & RBAC only | Auth & RBAC + minimal Settings UI (property, rooms, rate plans, CM creds, users, SMTP) |
| MVP duration | 10 weeks | 12 weeks |
| MVP go-live (M8 ★) | End of Month 2.5 (Week 10) | End of Month 3 (Week 12) |
| Settings module in Phase 1 | Build from scratch in Phase 1 sprint 1 | Extend the MVP Settings UI — add bulk import, audit log, advanced config. Less work in Phase 1. |
| M0 milestone | Kick-off only | Kick-off + data collection workshop. Ops Champion attends with room list, rates, API keys. |

# 2. Revised MVP — 3-Month Delivery Sequence

The MVP now runs for 12 weeks across 3 months. Every week has a named deliverable, clear owner, and explicit dependency on what was built the week before. The Settings UI built in Week 1 is the foundation that unlocks every subsequent sprint.

| Week | Deliverable | Owner | Done means… |
| --- | --- | --- | --- |
| Month 1 — Foundation |  |  |  |
| Week 0 | Kick-off & data collection | PM + Ops Champion + Tech Lead | - Project kick-off: team assembled, repo created, environments provisioned, design system tokens committed - Ops Champion workshop: collects and delivers room list (code, type, bed config, capacity) for all pilot-property villas, rate plans per room type (IDR nightly rates), Cloudbeds/Guesty API credentials (key + workspace ID), list of staff to create as users - PM confirms pilot property selection and go/no-go criteria for UAT - Tech Lead finalises DB schema for: properties, rooms, rate_plans, users, roles - Exit criteria: all property data delivered in agreed template (CSV/JSON) — engineers blocked without this |
| Week 1 | Auth + RBAC + minimal Settings UI | Engineering (FE + BE) | - Login screen: username/password, JWT, session (30-min idle timeout for Front Desk) - RBAC: Front Desk and Property Manager roles fully enforced server-side - Settings — Property: create/edit property record (name, address, timezone WITA, currency IDR, CI/CO times) - Settings — Rooms: add/edit/deactivate room (code, type, bed config, max occupancy); list view with status badge - Settings — Rate plans: create/edit rate plan tied to room type (IDR per night); effective date range - Settings — Channel manager: enter and verify Cloudbeds/Guesty API key + workspace ID; connection test button - Settings — Users: invite user (name, email, role, property assignment); deactivate user - Settings — SMTP: configure outbound email sender (host, port, from address); send test email - Ops Champion enters all data collected in Week 0 into the live Settings UI — pilot property fully seeded by end of Week 1 - Exit criteria: System Admin can log in, configure a complete property, and see all rooms listed |
| Week 2 | Reservation list (read-only) | Engineering (BE + FE) | - Channel manager read integration: pull today's arrivals and all active reservations from Cloudbeds or Guesty - Reservation list screen: filter by date, status (Expected, Checked In, Checked Out), room - Reservation detail card: guest name, contact, room assigned, dates, nights, source, special requests - Room mapping: reservations matched to rooms seeded in Week 1 Settings - Sync status indicator: last sync timestamp, error alert if sync fails - Exit criteria: Front Desk staff can see today's arrivals with correct room assignments pulled from real channel manager data |
| Month 2 — Core Workflows |  |  |  |
| Week 3 | Room status board | Engineering (FE + BE) | - Visual room grid: all rooms at pilot property, colour-coded by status (Available/Occupied/Dirty/Cleaning/Inspect/OOO) - Manual status update: Front Desk or Manager can change any room status with one tap - Status pulls room list from Settings — no hardcoded rooms - Auto-status on check-in: room → Occupied; auto-status on check-out: room → Dirty - Filter by status; last-updated timestamp per room - Exit criteria: room status board is live with real pilot-property rooms; Front Desk can update status and change is immediately visible |
| Weeks 4–5 | Check-in wizard | Engineering (FE + BE) | - Step 1 — Guest lookup: search reservation by name, booking ref, or arrival date; pre-populates guest card from channel manager data - Step 2 — Room assignment: room picker shows only Available (Clean) rooms; warns if selected room is Dirty or Inspect; pull room list from Settings - Step 3 — Guest count & ID: confirm number of adults/children; note ID number (text field, no scan required in MVP) - Step 4 — Special requests: pre-filled from reservation; editable; urgent flag if request is time-sensitive - Step 5 — Confirm: room flips to Occupied; reservation status → Checked In; timestamp recorded - Early CI handling: agent shown warning if room not ready; can override with manager approval note - No-show flow: mark reservation as No-Show after configurable cutoff; room returned to Available - Exit criteria: full 5-step check-in completable for a real arriving guest; room status updates correctly |
| Week 6 | Guest folio | Engineering (BE + FE) | - Folio creation: auto-created on check-in; accommodation line auto-posted using rate plan × nights (from Settings rate plans) - Manual charge posting: Front Desk can add ad-hoc line (description + amount); category selector (Room service, Transport, Misc) - Charge void: void with reason; requires manager approval if amount exceeds configurable threshold - Running balance: folio shows total charges, total payments, and balance due at all times - Folio visible from reservation detail card and check-in/out screens - Audit trail: every folio change logged (who, when, what changed) - Exit criteria: for a live checked-in guest, folio shows correct accommodation charge and agent can add/void a manual charge |
| Week 7 | Cash payment & check-out | Engineering (FE + BE) | - Payment recording — cash: agent enters amount tendered; system calculates change; payment recorded on folio - Partial payment: record deposit or partial settlement; balance updates in real time - Check-out workflow: open folio → add last-minute charges → collect payment → confirm check-out - Receipt generation: PDF receipt with property logo, itemised charges, payment summary, date - Receipt email: send to guest email via SMTP configured in Settings - Room status on check-out: auto → Dirty - Reservation status: → Checked Out; timestamp recorded - Exit criteria: complete check-out cycle executable for a real guest with receipt emailed; room flips to Dirty |
| Month 3 — Validate & Go-Live |  |  |  |
| Week 8 | Hardening & bug fix sprint | Engineering + QA | - QA regression pass: all MVP flows tested end-to-end on staging environment with real pilot-property data - Performance check: check-in wizard < 500ms response on all steps; room status board < 2s load - Edge cases: no-show, early CI, folio void, partial payment, room reassignment mid-stay - Settings validation: attempt to misconfigure a property and confirm the system blocks gracefully - All critical and high bugs resolved; medium bugs triaged with fix-by dates - Staging environment mirrors production — same AWS Jakarta region, same data - Exit criteria: zero open critical/high bugs; QA sign-off on all MVP flows |
| Week 9 | UAT at pilot property | PM + Ops Champion + real staff | - Parallel run begins: real guests checked in/out using VillaOps while paper process runs alongside as backup - Front Desk staff operate the system independently — facilitator observes, does not assist - Issues logged in real time; PM triages daily; critical issues fixed same day by engineering - Shift reconciliation: manager reviews folio totals vs physical cash at end of each shift - Staff pulse survey at end of Week 9: rate ease of use 1–10 - Exit criteria: all arriving guests processed through VillaOps; zero guests turned away due to system failure |
| Week 10 | Bug fix & UAT feedback | Engineering + PM | - All UAT-identified critical and high bugs resolved and deployed to staging - Quick-win UX improvements from staff feedback incorporated (label changes, error messages, flow tweaks) - Final QA regression on UAT fixes - Bilingual quick-reference laminated card (EN + ID) designed and sent to print - Go/no-go review meeting: PM + Ops Manager + Tech Lead review all 6 MVP success criteria - If go: production deployment plan confirmed. If no-go: 1-week extension with specific criteria to meet. - Exit criteria: go/no-go decision made with documented rationale |
| Week 11 | Production deployment & training | DevOps + PM + Ops Champion | - Production environment deployed to AWS ap-southeast-3 Jakarta; SSL active; monitoring live - All production Settings entries verified: rooms, rates, CM credentials, SMTP, user accounts - Full-staff training session: Front Desk (2 hours) and Property Manager (1 hour); bilingual delivery - Quick-reference card distributed to all reception stations - Rollback plan documented: conditions under which staff revert to paper; who authorises the call - Emergency contact list posted at reception (engineering on-call number, PM mobile) - Exit criteria: all staff trained; production environment verified; rollback plan confirmed |
| Week 12 ★ | MVP GO-LIVE | All stakeholders | - Paper check-in forms officially retired at pilot property — VillaOps is the only system - All arriving and departing guests processed exclusively through VillaOps - Engineering on-call for first 5 business days; response SLA: critical < 30 min, high < 2 hours - PM monitors success metrics daily: check-in time, folio discrepancies, system uptime, staff NPS - Daily stand-up for first 2 weeks: PM + Ops Champion + Tech Lead (15 min) - End of Week 12: preliminary success metric read; stakeholder update communicated |
| Week 13–14 | Monitored live run & retrospective | PM + Ops + Engineering | - Continued monitoring against all 6 MVP success criteria for 2 full weeks post go-live - Any remaining high bugs resolved; medium bugs scheduled into Phase 1 sprint backlog - MVP retrospective: what worked, what was painful, what to do differently in Phase 1 rollout - Lessons learned documented and shared with full team - Phase 1 sprint plan reviewed, confirmed, and sprint 1 kick-off scheduled - Exit criteria: all 6 success criteria met for 2 consecutive weeks — MVP declared complete |

# 3. MVP Milestone Summary

The table below condenses all MVP milestones for at-a-glance tracking and stakeholder reporting.

| M# | Week | Milestone deliverable | Owner |
| --- | --- | --- | --- |
| M0 | Week 0 | Kick-off complete. All property data collected from Ops Champion and ready for Settings entry. Blocker: engineers cannot start W1 Settings UI without room list and rate data | PM + Ops Champion + Tech Lead |
| M1 | Week 1 | Auth, RBAC (2 roles), and minimal Settings UI live in dev. Pilot property fully seeded. New milestone — did not exist in v1.0 | Engineering |
| M2 | Week 2 | Reservation list live: today's arrivals visible from real Cloudbeds/Guesty data. | Engineering |
| M3 | Week 3 | Room status board live: all pilot-property rooms visible with real-time status. | Engineering |
| M4 | Weeks 4–5 | Check-in wizard: 5-step flow end-to-end; room flips Occupied on completion. | Engineering |
| M5 | Week 6 | Guest folio: auto-posting accommodation charges, manual charge add/void, audit trail. | Engineering |
| M6 | Week 7 | Cash payment + check-out: full cycle executable; receipt PDF generated and emailed. | Engineering |
| M7 | Week 8 | Hardening sprint: zero critical/high bugs; QA sign-off on all MVP flows. | Engineering + QA |
| M8 | Week 9 | UAT at pilot property: all real guests processed through VillaOps; parallel run with paper. | PM + Ops Champion |
| M9 | Week 10 | UAT feedback resolved; go/no-go decision made; production deployment plan confirmed. | PM + Engineering |
| M10 | Week 11 | Production deployed; staff trained; rollback plan documented; monitoring live. | DevOps + PM + Ops Champion |
| M11 ★ | Week 12 | MVP GO-LIVE — paper process retired. VillaOps is the only check-in/out system at pilot property. | All stakeholders |
| M12 | Weeks 13–14 | MVP retrospective complete. Phase 1 sprint 1 kicked off. All 6 success criteria met. | PM + Ops + Tech Lead |

# 4. Minimal Settings UI — Option B Scope (Week 1)

The Settings UI built in Week 1 is intentionally minimal — only what is required for the MVP to function. It is not the full Settings module from the PRD. In Phase 1, this shell is extended with bulk import, advanced configuration, audit log viewer, and all-property management. The Week 1 build is the foundation, not the destination.

## 4.1 Settings screens in scope for Week 1 (MVP)

| Screen | Fields / actions | Used by | Used from |
| --- | --- | --- | --- |
| Property | Name, address, timezone, currency, CI time, CO time, logo upload (optional) | System Admin | Week 1 |
| Rooms / Villas | Add / edit / deactivate room: code, type, bed config, max occupancy, description (optional) | System Admin | Week 1 → Room board Week 3, Check-in Weeks 4–5 |
| Rate plans | Create rate plan: name, room type, IDR/night, effective date range; list and edit existing | System Admin | Week 1 → Folio Week 6 |
| Channel manager | Select CM (Cloudbeds / Guesty / SiteMinder), enter API key + workspace ID, test connection button, sync status | System Admin | Week 1 → Reservations Week 2 |
| Users | Invite user: name, email, role (Front Desk / Manager), property assignment; deactivate; reset password | System Admin | Week 1 → UAT Week 9 |
| SMTP / Email | Outbound email: host, port, username, from address, from name; send test email button | System Admin | Week 6 → Receipt email Week 7 |

## 4.2 Settings screens deferred to Phase 1

| Screen | Why deferred | Phase 1 sprint |
| --- | --- | --- |
| Multi-property management | MVP covers only one pilot property. Portfolio view needed when rolling out to all 5 properties. | Sprint 1 |
| Room bulk import (CSV) | Pilot property has few enough rooms to enter manually. Bulk import saves time for Phase 1 portfolio rollout. | Sprint 1 |
| HK task checklists | Housekeeping module not in MVP. Checklist config needed before HK module ships. | Sprint 2 |
| Room service menu | Room service module not in MVP. Menu config needed before RS module ships. | Sprint 3 |
| Folio void threshold config | Threshold can be hardcoded to IDR 500,000 for MVP. Configurable field added in Phase 1. | Sprint 1 |
| Audit log viewer | Audit trail is written from Week 6 onward. Viewer UI (search, filter, export) is a Phase 1 reporting concern. | Sprint 5 |
| All 7 roles in Users screen | MVP creates only Front Desk and Manager. HK, Maintenance, F&B, Owner, Admin roles added when those modules ship. | Sprint 1 |

# 5. MVP Success Criteria

Unchanged from v1.0. All 6 criteria must be met for 2 consecutive weeks starting from Week 12 go-live before MVP is declared complete.

| Criterion | Target | Measured by |
| --- | --- | --- |
| All daily check-ins processed through VillaOps | 100% | Operation log audit |
| Zero paper check-in forms used | 0 forms | Physical spot check |
| Average check-in time per guest | < 5 minutes | System timestamp delta |
| Folio balance discrepancies (per week) | < 2 / week | Shift reconciliation |
| Staff NPS after 2 weeks live | ≥ 7 / 10 | Pulse survey |
| System uptime (monthly) | ≥ 99% | Server monitoring |

# 6. Updated Master Gantt

The MVP now occupies Months 1–3 (12 weeks). Phase 1 begins Month 4. Phase 2 from Month 9. The Settings UI workstream (new) is shown as the first row.

| Workstream | MVP (M1–3) |  |  | Phase 1 (M4–8) |  |  |  |  | Phase 2 (M9–18) |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Month → | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 |
| Settings UI — Option B (NEW) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Auth, RBAC & reservation list |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Room status board |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Check-in wizard |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Guest folio & cash payment |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Check-out & receipt email |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Hardening, UAT & go-live |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 2-way channel sync (all 3 CMs) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Payments — card + QRIS |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Housekeeping module |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Room service module |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Laundry + transport modules |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Maintenance module |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Settings — Phase 1 extensions |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Bahasa Indonesia UI |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Reports suite + occ. dashboard |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Portfolio UAT & training |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Offline resilience |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Internal CM integration |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Mobile app (iOS + Android) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Push notifications |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Advanced analytics |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Guest QR room service menu |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| WhatsApp notifications |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Online payment link |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Accounting export |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Activities marketplace |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Custom report builder |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| ■ MVP (Months 1–3) ■ Phase 1 (Months 4–8) ■ Phase 2 (Months 9–18) ■ New workstream (v2.0) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |

# 7. Phase 1 & Phase 2 — Unchanged from v1.0

Phase 1 and Phase 2 scope, team structure, risk register, and feature backlog are identical to v1.0. The only downstream effect of the v2.0 revision is that the Settings module in Phase 1 Sprint 1 is now an extension of the MVP Settings UI, not a greenfield build — reducing sprint 1 effort by approximately 1 week.

## 7.1 Phase 1 — Full operations platform (Months 4–8)

Phase 1 adds all 9 PRD modules, all 5 properties, all 7 roles, Bahasa Indonesia UI, offline resilience, and the full reports suite. Key change from v1.0: Sprint 1 begins with extending the MVP Settings UI rather than building it from scratch.

| Module | Sprint | Status vs v1.0 |
| --- | --- | --- |
| Settings — Phase 1 extensions | Sprint 1 | Reduced scope — extends MVP UI. Multi-property mgmt, bulk room import, all 7 roles, folio void threshold config, audit log viewer. |
| 2-way channel sync | Sprint 1–2 | Unchanged |
| Card + QRIS payments | Sprint 1 | Unchanged |
| Housekeeping | Sprint 2–3 | Unchanged |
| Room service | Sprint 3 | Unchanged |
| Laundry + Transport | Sprint 4 | Unchanged |
| Maintenance | Sprint 3 | Unchanged |
| Bahasa Indonesia UI | Sprint 4 | Unchanged |
| Reports + occ. dashboard | Sprint 5 | Unchanged |
| Offline resilience | Sprint 5 | Unchanged |
| Portfolio UAT & training | Sprint 6 | Unchanged |

## 7.2 Phase 2 — Extended platform (Months 9–18)

Phase 2 scope is identical to v1.0 across all 4 streams: mobile app (A1–A5), guest-facing features (B1–B5), integrations including internal channel manager (C1–C4), and advanced analytics (D1–D4). Refer to v1.0 for full feature backlog and priority ratings.

# 8. Open Questions — Updated for v2.0

Most open questions from v1.0 remain. Two new items added for the Settings UI and data collection.

| # | Question | Options | Deadline | Owner |
| --- | --- | --- | --- | --- |
| 1 | Which property is the MVP pilot? | Select one with stable connectivity and willing staff champion | Week 0 | Ops Manager |
| 2 | Which channel manager is integrated first for MVP? | Cloudbeds (recommended) / Guesty | Week 0 | Product + Ops |
| 3 | Cloud region for hosting? | AWS ap-southeast-3 Jakarta (recommended) / Singapore | Week 0 | IT / Legal |
| 4 ★ | Who is the Ops Champion and are they available full-time in Week 0 for the data collection workshop? | Must be someone with room lists, rate cards, and CM API access — not a task for junior staff | Week 0 | Ops Manager |
| 5 ★ | Can room list and rate plans be supplied in a CSV template by end of Week 0? | Engineering provides the template in kick-off; Ops Champion fills and returns within 3 business days | Week 0 | Ops Champion |
| 6 | Folio void approval threshold? | IDR 100K / 500K / configurable — hardcoded to 500K for MVP, configurable in Phase 1 | Week 1 | Finance |
| 7 | Faktur Pajak: built-in or external accounting? | Built-in (adds 2 sprints) / external accounting software | Week 1 | Finance / Legal |
| 8 | Single shared instance or separate per property? | Single instance (recommended) / separate instances | Week 1 | IT / Architecture |
| 9 | Internal CM API spec for Phase 2 planning? | Share API docs by Month 3 | Month 3 | Tech Lead |

# 9. Success Metrics Scorecard

Unchanged from v1.0. Tracked at three checkpoints: MVP go-live (Week 12), Phase 1 go-live (Month 8), and 6 months post Phase 1.

| Metric | Baseline | MVP target | Phase 1 target | 6 months post-P1 |
| --- | --- | --- | --- | --- |
| Check-in time per guest | 8–12 min | < 5 min | < 4 min | < 3 min |
| Untracked charges / month | 15–20 | < 8 | < 2 | 0 |
| Paper forms used / day | 20–30 | 0 at pilot | 0 portfolio | 0 |
| HK task completion rate | ~75% | Not tracked | > 95% | > 97% |
| Room service SLA (on-time %) | Not tracked | Not tracked | > 80% | > 90% |
| Billing dispute resolution | 2–4 days | < 1 day | < 4 hours | < 2 hours |
| Staff onboarding time | 3–5 days | < 2 days | < 1 day | < 4 hours |
| System uptime (monthly) | N/A | ≥ 99% | ≥ 99.5% | ≥ 99.5% |
| Owner dashboard satisfaction | N/A | N/A | ≥ 7/10 | ≥ 8/10 |

End of document — VillaOps Milestone, Phase & MVP Plan v2.0